# Area H6 Toastmasters International & Table Topic Contest To-Do List

| # | Things to do | DY | OL | VT | II | QW | TS | SL | #### TY | #### Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | ### Fix venue, date and time | X | X |  |  |  |  |  |  | Done |
| 2. | Find and confirm: a. Contest Chair: b. Chief Judge & Judges - 2 Trophies – two for Champions, 3 books - two for 1st runner-ups, one for 2nd runner-ups | X X |  | X |  | X |  |  |  | Done ? Done |
| 3. | 3 weeks before the contest: a. Find Helpers: 2 Time-Keepers, 2 Ballot Counters & 2 SAA + 3 Receptionists. b. Inform each individual club to take charge of ticketing & enrolment - Find coordinators for collecting money and submission of name list. - Prepare flyer for promotion. - Confirm with venue: Banner (with Amana’s help) seating arrangements, mic, O/H projector, stage, etc - Prepare a list of participants (target 120). - Prepare the budget. | X X X X X | X X X X | X X X X | X X X | X | X |  |  | Done Done Done Done Done ? ? Done |
| 4. | 2 weeks before the contest: a. Site visit & rehearsal on 16 March. Make sure all equipments needed to be ready. | X | X | X | X | X | X | X | X | Done |
| 5. | 1 week before the contest: - Collect names of contestants and pass it to Contest Chair. (South Horizons 09 Mar, Centraler 06 Mar, Kowloon 13 Mar, TGIT 22 Feb) Collect all contestant biographical information. - Make a list of all equipments contestants needed and coordinate with venue - Prepare questions for interview session - Confirm helpers: Time-keepers (2), ballot counters (2) & SAA (2). Arrive at the venue at 1:30pm. - Confirm contestants. Make sure they will be there at 2:15pm to test the equipment, be briefed and draw lots. - Confirm with Presidents that they will bring flags to the venue. - Confirm photographers. - Find timer (check with Florence), color cards & / or traffic lights. - Find calculators, lucky draw boxes, tapes for signages, banner - Make sure the chief judge knows that he needs to brief all the judges. - Prepare programs, judging criteria, judge’s guidelines, etc. - Send out programs to contestant and post it on website. - Send out judging criteria, judge’s guidelines, etc. - Finalize the budget. - Prepare signages: 7 Contestant, 1 Contest Chair, 2 Timer, 1 ‘Contest is in progress. Please wait for a while.’ + ‘ Please use another door.’ - Prepare name badges for all volunteers. - Prepare logistics for ‘Guess who’s the winner’. - Pack and order 2 trophies and 7 books with 7 ribbon flowers - Prepare certificates of appreciation to all judges and OC members - Prepare certificates of participation to all contestants - Prepare 5 award certificates(2 for champion,2 for 1st runner-up, 1for 2nd runner-up) | X X X X X X | X X | X X X X | X X X X X | X |  | X | X X X | Done ? Done ? ? ? Done Done Done ? ? ? ? ? ? ? ? ? ? ? ? ? |
| 6. | 3 day before the contest: a. Print the participants’ list (In alphabetical order with payment status). b. Photocopy 80 Contest programs with who’s winner, 80 judging criteria, 80 judge’s guide and ballot, 2 tie-breaking judge’s guide and ballot, 3 time record sheet and instructions for timers, 3 counters’ tally sheet (SC) - Prepare stationary: tapes, pens, papers, club flags, banner, - Print all certificates (DY) | X | X X | X | X |  |  | X |  | ? ? ? ? |

## Core Group Directory

| Deborah Yu (DY): Area H6 Governor | 8222 0989 | Deborah_Sharon_yu@I-cable.com |
| --- | --- | --- |
| Oliver Lau (OL): Contest Organiser | 9174 5983 | Oliverlau_contest@hotmail.com |
| Veronica Tsang (VT): Floor Manager | 9677 4882 | vero@ctimail.com |
| Iris Ie (II): IT Manager / Timer | 9439 7910 | Iriskie@yahoo.com |
| Queenie Wong (QW): Assist Area Governor – E&T | 9670 4466 | Queenie2601@yahoo.com |
| Tafline Yew : Contest Chair | 9273 9363 | Taffy@netvigator.com |
| Tony Smithseree (TS): Registration Manager | 9758 3602 | verobiz@netvigator.com |
| Salina Luk (SL): SAA | 9469 0371 | salina@orngchan.com |
| Martha Chan (MC): Treasurer | 9336 6790 | Chanmartha@yahoo.com |
| Florence Hui (FH): Receptionist | 9659 6999 | Shui@sairgroup.com |
| Rowenaa Chan : Ballot Counter | 9458 9908 | rowenaa@netvigator.com |
| Chris Lai: Ballot Counter | TBA |  |
| Rita Lee : Timer | 9452 5500 | ritaleesf@hotmail.com |
| ##### Christine Lau : Reception | 9837 9934 | CLau@triu.com |
| Sam Chiu : Floor & SAA | 8200 3548 | Ali308@netvigator.com |
| Simon Cheng : Floor & SAA | 2331 4755 | Simon.cheng@tnt.com |